| Project year | Months, activities, responsible partners |  | Months, activities, responsible partners |  | Months, activities, responsible partners |  | Months, activities, responsible partners |  | Months, activities, responsible partners |  | Months, activities, responsible partners |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2015-2016 | Sep 2015 |  | Oct 2015 |  | Nov 2015 |  | Dec 2015 |  | Jan 2016 |  | Feb 2016 |  |
|  | Announcement of the project approval to the school staff/community |  | 1st transnational project meeting (Bulgaria) |  | Designing project display boards/Erasmus+ corners in all partner schools |  | Teachers` virtual mobilitiy |  | Lesson plans` creation |  | Teachers` virtual mobilitiy |  |
|  | Project`s information day in all schools |  | Website set up |  | Designing, publishing and printing the project`s newsletter |  | Students` virtual mobilitiy |  | Monitoring and evaluation |  | Designing, publishing and printing the project`s newsletter |  |
|  | European Day of Languages |  | Creating the project`s TwinSpace |  | Students` activities |  | Monitoring and evaluation |  | Students` activities |  | Teachers` activities |  |
|  | Modifying the school project teams, if needed |  | Drafts of all major reports and management, implementation, communication and dissemination plans |  | Monitoring and evaluation |  | Teachers` activities |  | Website update |  | Monitoring and evaluation |  |
|  | Media communication, press releases, articles |  | Creating and printing questionnaires, surveys, assessment, self-assessment and other relevant evaluation forms |  | Project`s web presence through social networks and on-line media |  | Work on the e-platform |  | TwinSpace update |  | Work on the e-platform |  |
|  | Project`s web presence through social networks and on-line media |  | Creating e-mail lists of stakeholders and interested parties (network of contacts) |  | Website update |  | Website update |  | Project`s web presence through social networks and on-line media |  | Short-term joint staff training |  |
|  | Teachers` virtual mobilitiy (eTwinning, FB, Skype, e-mails |  | Students` virtual mobility |  | TwinSpace update |  | TwinSpace update |  |  |  | Website update |  |
|  |  |  | Monitoring and evaluation |  |  |  | Project`s web presence through social networks and on-line media |  |  |  | TwinSpace update |  |
|  |  |  | Project`s web presence through social networks and on-line media |  |  |  |  |  |  |  | Project`s web presence through social networks and on-line media |  |
|  |  |  | Media communication, press releases, articles |  |  |  |  |  |  |  |  |  |
|  |  |  | Teachers` activities: lesson plans` preparation, creating/importing content into the e-platform, designing practical maths tasks/problems, planning and implementing cross curricular projects |  |  |  |  |  |  |  |  |  |
|  | Mar 2016 |  | Apr 2016 |  | May 2016 |  | Jun 2016 |  | Jul 2016 |  | Aug 2016 |  |
|  | World Mathematics Day in all partner schools |  | Teachers` virtual mobilitiy |  | Europe Day in all partner schools |  | 2nd transnational meeting (Lithuania) |  |  |  |  |  |
|  | Students` activities |  | Students` virtual mobility |  | Lesson plans` creation |  | Teachers` virtual mobilitiy |  |  |  |  |  |
|  | Monitoring and evaluation |  | Presentations and demonstrations at workshops organized by the partners in all partner schools |  | Monitoring and evaluation |  | Designing, publishing and printing the project`s newsletter |  |  |  |  |  |
|  | Website update |  | Monitoring and evaluation |  | Students` activities |  | Teachers` activities |  |  |  |  |  |
|  | TwinSpace update |  | Teachers` activities |  | Website update |  | Work on the e-platform |  |  |  |  |  |
|  | Media communication, press releases, articles |  | Work on the e-platform |  | TwinSpace update |  | Monitoring and evaluation |  |  |  |  |  |
|  | Project`s web presence through social networks and on-line media |  | Website update |  |  |  | Website update |  |  |  |  |  |
|  |  |  | TwinSpace update |  |  |  | TwinSpace update |  |  |  |  |  |
|  |  |  | Media communication, press releases, articles |  |  |  | Media communication, press releases, articles |  |  |  |  |  |
|  |  |  | Project`s web presence through social networks and on-line media |  |  |  |  |  |  |  |  |  |