Report

on the 1st Transnational Project Meeting in Targovishte, Bulgaria

13th – 15th October 2015

The 1st Transnational Project Meeting of Active, Attractive And Interactive eU Mathematics, Erasmus+ project, was an event that brought together participants from 7 (out of 9) partner schools involved in this strategic partnership. Representatives of the German and French partner institutions took part in some sessions of the meeting through Skype.

Participating teachers:

| N | Name | Institution | Country |
| --- | --- | --- | --- |
| 1. | ##### Marijana Zarožinski | Industrijsko-obrtnička škola-Slavonski Brod | Croatia |
| 2. | Ines Delhusa | Industrijsko-obrtnička škola-Slavonski Brod | Croatia |
| 3. | Alessia Cazzola | Istituto Professionale Statale per l'Industria e l'Artigianato-Cernusco sul Naviglio | Italy |
| 4. | Marina Calcagno | Istituto Professionale Statale per l'Industria e l'Artigianato-Cernusco sul Naviglio | Italy |
| 5. | Maria Montserrat Cueto Garcia | IES PAU CASESNOVES-Inca | Spain |
| 6. | ##### Ester Martinez Luceño | IES PAU CASESNOVES-Inca | Spain |
| 7. | María José Baena Morata | IES PAU CASESNOVES-Inca | Spain |
| 8. | Gil Nunes | Agrupamento de Escolas de Abação-Guimarães | Portugal |
| 9. | Jorge Novais | Agrupamento de Escolas de Abação-Guimarães | Portugal |
| 10. | Lauri Vilibert | Tallinna Kristiine Gümnaasium-Tallinn | Estonia |
| 11. | Anu Reha | Tallinna Kristiine Gümnaasium-Tallinn | Estonia |
| 12. | Rūta Krikštopaitienė | Sakiu rajono Lekeciu mokykla-Sakiai | Lithuania |
| 13. | Rimanta Poderyte | Sakiu rajono Lekeciu mokykla-Sakiai | Lithuania |
| 14. | Sevdalina Zafirova | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 15. | Ivalina Kostova | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 16. | Boryana Boteva | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 17. | Darina Rusinova | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 18. | Violeta Ruseva | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 19. | Mariana Despodova | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 20, | Galina Kostadinova | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 21. | Tyurkyan Isufova | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |
| 22. | Kinka Doncheva | SOU “Sveti Sedmochislenitsi”-Targovishte | Bulgaria |

Meeting objectives:

-For all partners to meet, become acquainted to the project, discuss important issues and significant matters in regards to the realization of the project; -To rearrange some of the activities in the timetable; -To strengthen the commitment of all partner schools; -To share experiences, challenges and technical knowledge on how to better carry out the planned activities; -To discuss future agreements regarding the short-term joint staff training in Estonia and the 2nd transnational project meeting in Lithuania; -To discuss the evaluation and dissemination; -The roles and tasks of each institution in this partnership; -Budget issues. Preparation: The coordinating school made practical arrangements, such as booking the hotel, preparing the agenda, sending the official invitation, providing information on how to travel from the airport to the meeting venue, etc. Participants made travel arrangements: booking flights, buying insurance, preparing all the necessary information and presentations for the meeting. Meeting minutes: Tuesday, October 13th; 08.30, in front of the hotel Excursion to the town of Veliko Tarnovo and the village of Arbanasi The guests have visited places of historical and cultural interest.. Wednesday, October 14th; 09.00-09.15 Welcome ceremony The official opening of the 1st Transnational Project Meeting was held in the Our Europe school foyer and included: -speeches by Sevdalina Zafirova, school headmaster, and Boryana Boteva, project coordinator; -greetings (songs) by students from the school. 09.15-10.00 Walking around the school (Part 1) The host school was presented through walking around it, entering some classrooms, meeting some teachers and students, visiting the mathematics and science school centre, visiting school areas dedicated to the European Union and previous international projects. 10.00-12.00 Work session 1: - Partners` schools presentations In free form (film/video, pictures slideshow, PowerPoint,…,5 min per school) the partners introduced their own institutions. The self-introduction confirmed the fact that the partnership is composed of members of quality and with rich experience in the subjects of the project. - 1st year project`s implementation outputs As outputs of the 1st year project`s implementation, it was stated that the partners are going to produce and achieve a set of products and results, which could be categorized as: 1. Events and event-related materials: - Project`s Information Day in all partner schools in the 1st project`s month; - World Mathematics Day in all schools; - Europe Day in all schools; - Mathematics festivals and competitions in all schools; - Festival scenarios; - Lists of mathematical tasks/problems; - Mathematics competitions` rules and tasks; - Workshops organized in all schools to present the project and disseminate its outcomes; 2. Material production out of events: - Presentations at meetings and publications in the partner schools` websites/newsletters to inform school staff and stakeholders about participation in external events; - Project`s website posts. 3. Project strategic documentation: - Work plan; - Dissemination strategy. 4. Reports, summaries and minutes: - Interim report; - Evaluation reports and other documentation (assessment and evaluation forms, surveys, questionnaires, etc.); - Monitoring reports; - Summaries of the transnational project meetings; - Staff and team meetings` minutes. 5. Project website, containing the following information: - Project description; - All public deliverables; - Project informational materials (newsletters, brochures, publications); - Information on project events; - Description of project partners, including links to partner websites. - Links to funding agencies, relevant projects and organisations; - Forum section; - Gallery; - Students` corner. It will be designed and maintained by the coordinator and updated continuously and collaboratively. 6. Project`s web presence: - Facebook page for communication, information and dissemination purposes; - YouTube channel-project`s attractiveness, visualization and dissemination. 7. Project`s TwinSpace, used as a communication, collaboration and dissemination virtual platform by directly involved in the project activities teachers and students. 8. Exchange of ideas and good practice related to: - ICT-based tools and content in teaching/learning mathematics; - Increasing students` learning motivation. 9. European cooperation: - Transnational sharing of experience and best practice; - List of websites to be used from teachers and students in teaching and learning mathematics; - Networks of contacts - e-mail lists of stakeholders and interested parties (for each partners and joint for the partnership). 10. Records and visuals: - Project display board/Erasmus+ corner in the partner schools; - Project log book (diary) in e-form, carried out by international students` team; - Art work exhibition: drawings, posters, models, in all partner schools; - Photographs/web albums; - Videos and short films; - Record of project`s expenses. 11. Promotional and informational materials and products: - Project newsletters (electronic and printed form); - Press releases and articles in the local media, newspapers, thematic magazines; - Radio and TV broadcasts; - Project logo and slogan, created by students. - Project management, guiding and monitoring the project`s implementation Significant aspects of the project that relate to the management, coordination and smooth realisation of all activities and keeping of necessary files and documents were discussed in details. It has been agreed that the first budget transfer (40%) is going to be made after the bilateral contracts` being signed. The second budget part (40%) will be transferred after the submission of the interim report. The third (final) transfer (20%) will be carried out after the acceptance of the final report. The budget has been discussed item by item as well as all the eligible costs. It has been stressed that the partners must keep records of all expenditure and give/send copies of all documents to the coordinating school. The budget for the planned mobilities is, in general cases, insufficient. Two solutions were proposed: either the amount of 575/760€ can be supplemented out of the management costs or the partner institution supplements the amount from its budget. Budget for the Intellectual outputs: what is needed is a document showing the legal relationship between the partner institution and the expert to be paid and the usual time sheets. A financial manager, who will work with the school`s accountancy office, will be appointed in each partner school and will be responsible for the budget control and financial management, as follow: - To keep regular checks on the incomings and outgoings of the project. Monthly bank statements and receipts for all transactions (travel, accommodation etc.) will be kept for monitoring purposes and copies-sent to the project coordinator; - To keep a record of expenses during the contract period; - To establish an efficient financial reporting system; - To control the eligibility of expenditure; - To ensure that the necessary documentation is provided. In regards to the project management and monitoring, the partners decided to: - Review the work plan on a regular basis to determine how we are progressing in terms of schedule and budget. For our project the review frequency is every month; - Identify activities that have been completed during the previous time period and update the work plan, if necessary; - Determine whether there are any other activities that should be completed but have not been; - After the work plan has been updated, determine whether the project will be completed within the original effort, cost, and duration. If not, we will have to look for ways to overcome the obstacles and solve the problems we have faced. 12.15-13.30 Lunch 14.00-15.30 Work session 2: - Presenting the web-based Maths teaching and learning in the partners` schools as well the software used by the teachers to create Maths content Teachers from all participating schools have presented educational sites as well software used in their institutions to create Maths content. The teachers also shared experience and good practices in web-based Maths teaching and learning. At the end of the day, a list of useful sites has been jointly created. - Reviewing and approving/improving of the work plan for the 1st project year All partner schools were given a list of their tasks and responsibilities, as stated in the application form, as well as a chart with all the activities which have to be carried out during the 1st project year. A special attention was paid on the 1st and 2nd project month`s activities. We had to change our plans due to objective reasons: The Bulgarian school undertakes the responsibility for creating and administrating the e-learning platform instead of the Estonian partner, as it was planned in the application form. 15.30-15.45 Coffee break 15.45-17.00 Work session 3: Communication and dissemination plans` updates It was decided that the dissemination plan will be in a matrix: №; What?; To whom?; How to do it?; When?; Resources. -human -financial -materials -…. Many different channels and mechanisms for communication and dissemination the project are going to be used within the partnership: - Networking; - Social media; - Newsletters; - Flyers and brochures; - Face to face; - Presentations at different meetings, seminars and conferences which representatives of the partner institutions attend; - Press conferences; - Promotional materials and products; - Presentations on exhibitions, fairs, etc.; - Project website; - Dedicated workshops, conferences, etc.; - Schools` newspapers and websites; - Articles and press releases; - European data basis; - Radio/TV broadcasts. The common communication plan has been revised during the meeting: regular communication on the eTwinning platform and in the Facebook group space, e-mail exchanges, feedback on the actions carried out locally, report submission deadlines, etc. We have negotiated that the contact persons should reply to all messages and posts within three days. Communication amongst partners will be carried out at least once a week. 19.00 Farewell dinner. Thursday, October 15th; 08.45 Meeting in the lobby of the hotel and walking to the school 09.00-10.00 Walking around the school (Part 2) The guest teachers continued their walking around the school, visiting some other classrooms and observing parts of web-based Mathematics, Physics and Chemistry lessons (Windows Envision: Multiply mice on one computer-educational software created by Bulgarian teachers and IT specialists; virtual labs). 10.00-12.00 Work session 4: - Planning the evaluation strategy The evaluation plan has been elaborated in details at the meeting. We take some important decisions: - During each meeting we will evaluate work, interaction and outputs; - We will take into account the number of activities completed in comparison with the number planned; - Each country will be allocated a specific task from which it has to report back at each meeting; - The students will be required to give a feedback of their work in the project; - Questionnaires will be filled in after each project visit, after certain activities and after each year of the cooperation. In accordance with our strategy, we are going to evaluate the progress in the achievement of the objectives on the basis of outputs and results indicators; level of effectiveness and efficiency of the project`s implementation; quality of the management and coordination; teachers’ cooperation and team work; level of acceptance/adoption of project outputs. - Establishment of quantity and quality indicators for the partnership`s success and impact The partners have negotiated on a set of indicators in order to measure outputs and results, performance and impact of the project. It was decided that the numbers of stakeholders` positive opinions, presentations, visits on the website, presentations at workshops, project materials and products made by students; dissemination of the project results in the local media; collaboration with local authorities and other organisations will be discussed at the project meetings and used as evaluation indicators. We negotiated to evaluate the partnership through different methods: evaluation reports, project descriptions minutes/synopsis of meetings, discussions, interviews, questionnaires, surveys, observations, pre- and post-testing (at the beginning and end of a project activity, to measure improvement in understanding/knowledge/attitude), comments section on the project website or in social networks. All the indicators were revised and placed in a list and given to the partners. 12.15-13.30 Lunch 14.00-16.00 Work session 5: - Planning the virtual mobilities and the students` involvement in the project activities Nevertheless the students` exchanges we applied for have not been approved, we confirmed student`s active involvement in the project activities. The pupils will take part in different activities on a local level, as planned in the application form. They will also carry out virtual mobilities in the project`s TwinSpace. More effective and detailed mobilities` planning is going to be made after creating the TwinSpace by the German and Portuguese partners. - Planning the teachers` training event in Estonia The partners agreed on the dates for the short-term joint staff training which is going to take place in the Estonian school from the 14th to the 20th of February 2016. There are no changes in the planned number of participants. There was a discussion about what subjects’ teachers can participate-Maths, IT (support), English (translators)… The issue is still open. The Estonian school is in charge of creating the event programme. The preparation will go on through e-channels. Free evening.