## Foglio1
Lavori per il progetto Erasmus+Math
Date | who | what | how long | Varie
2015-09-01 | Marina | First presentation of the project at the general teachers’ meeting held at the start of the new school year
2015-10-10 | Marina/Alessia | Preparation for the first meeting and of newspaper article
12 - 16/10/2015 | Marina/Alessia | Project meeting Bulgaria | 5gg
2015-10-20 | Marina/Alessia | Updating other school teaches about the meeting | 1h
2015-10-30 | Marina/Alessia/ | Financial meeting with Headmaster and Financial manager
2015-11-04 | Alessia/Giovanni | Planning the math lesons | 1h
2015-11-04 | Marina/Alessia | Designing of the project leaflet and project corner | 1h
2015-11-12 | Marina | Discussion with the students about the school film contents | 1h
2015-11-26 | Alessia/Marina/stud project corner |  | 1h
2015-11-28 | Marina/Alessia | Open Day presentation and distribution of the project leaflet | 1,5h
2015-12-14 | Alessia | Working at home on lessons plan | 2h
2015-12-15 | Alessia | Working at home on lessons plan | 2h
2015-12-21 | Marina/Alessia/Nicoletta/Stefano/Adelaide | Meeting with Headmaster for tasks redistribution after France withdrawl | 0,5h
2016-01-21 | Alessia/Giovanni | Working at power point | 1h
2016-02-03 | Alessia/Marina | Preparation material for newspaper article about the project | 1h
2016-02-04 | Alessia/Nicoletta | Working at excel for the lessons | 1h
2016-02-08 | Alessia | File excel translation | 1,5h
2016-02-09 | Marina7Alessia/Giovanni/Stefano | Preparation for project meeting in Estonia | 1h